## WBS Gantt Chart View
Project Plan | time axis 2023-01-23 to 2023-10-08
Finish Date | 2023-02-19
Duration | 27 | Day(s)
Start Date | 2023-01-23
WBS NUMBER | TASK TITLE | DESCRIPTION | TASK OWNER (Person In charge of task) | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE | 2023-01-23: WEEK 1; 2023-01-30: WEEK 2; 2023-02-06: WEEK 3; 2023-02-13: WEEK 4; 2023-02-20: WEEK 5; 2023-02-27: WEEK 6; 2023-03-06: WEEK 7; 2023-03-13: WEEK 8; 2023-03-20: WEEK 9; 2023-03-27: WEEK 10; 2023-04-03: WEEK 11; 2023-04-10: WEEK 12; 2023-04-17: WEEK 13; 2023-04-24: WEEK 14; 2023-05-01: WEEK 15; 2023-05-08: WEEK 16; 2023-05-15: WEEK 17; 2023-05-22: WEEK 18; 2023-05-29: WEEK 19; 2023-06-05: WEEK 20; 2023-06-12: WEEK 21; 2023-06-19: WEEK 22; 2023-06-26: WEEK 23; 2023-07-03: WEEK 24; 2023-07-10: WEEK 25; 2023-07-17: WEEK 26; 2023-07-24: WEEK 27; 2023-07-31: WEEK 28; 2023-08-07: WEEK 29; 2023-08-14: WEEK 30; 2023-08-21: WEEK 31; 2023-08-28: WEEK 32; 2023-09-04: WEEK 33; 2023-09-11: WEEK 34; 2023-09-18: WEEK 35; 2023-09-25: WEEK 36; 2023-10-02: WEEK 37
[8 empty] | 2023-01-23 | [6 empty] | 2023-01-30 | [6 empty] | 2023-02-06 | [6 empty] | 2023-02-13 | [6 empty] | 2023-02-20 | [6 empty] | 2023-02-27 | [6 empty] | 2023-03-06 | [6 empty] | 2023-03-13 | [6 empty] | 2023-03-20 | [6 empty] | 2023-03-27 | [6 empty] | 2023-04-03 | [6 empty] | 2023-04-10 | [6 empty] | 2023-04-17 | [6 empty] | 2023-04-24 | [6 empty] | 2023-05-01 | [6 empty] | 2023-05-08 | [6 empty] | 2023-05-15 | [6 empty] | 2023-05-22 | [6 empty] | 2023-05-29 | [6 empty] | 2023-06-05 | [6 empty] | 2023-06-12 | [6 empty] | 2023-06-19 | [6 empty] | 2023-06-26 | [6 empty] | 2023-07-03 | [6 empty] | 2023-07-10 | [6 empty] | 2023-07-17 | [6 empty] | 2023-07-24 | [6 empty] | 2023-07-31 | [6 empty] | 2023-08-07 | [6 empty] | 2023-08-14 | [6 empty] | 2023-08-21 | [6 empty] | 2023-08-28 | [6 empty] | 2023-09-04 | [6 empty] | 2023-09-11 | [6 empty] | 2023-09-18 | [6 empty] | 2023-09-25 | [6 empty] | 2023-10-02
[8 empty] | M | T | W | Th | F | S | Su | M | T | W | Th | F | S | Su | M | T | W | Th | F | S | Su | M | T | W | Th | F | S | Su | M | T | W | Th | F | S | Su | M | T | W | Th | F | S | Su | M | T | W | Th | F | S | Su | M | T | W | Th | F | S | Su | M | T | W | Th | F | S | Su | M | T | W | Th | F | S | Su | M | T | W | Th | F | S | Su | M | T | W | Th | F | S | Su | M | T | W | Th | F | S | Su | M | T | W | Th | F | S | Su | M | T | W | Th | F | S | Su | M | T | W | Th | F | S | Su | M | T | W | Th | F | S | Su | M | T | W | Th | F | S | Su | M | T | W | Th | F | S | Su | M | T | W | Th | F | S | Su | M | T | W | Th | F | S | Su | M | T | W | Th | F | S | Su | M | T | W | Th | F | S | Su | M | T | W | Th | F | S | Su | M | T | W | Th | F | S | Su | M | T | W | Th | F | S | Su | M | T | W | Th | F | S | Su | M | T | W | Th | F | S | Su | M | T | W | Th | F | S | Su | M | T | W | Th | F | S | Su | M | T | W | Th | F | S | Su | M | T | W | Th | F | S | Su | M | T | W | Th | F | S | Su | M | T | W | Th | F | S | Su | M | T | W | Th | F | S | Su | M | T | W | Th | F | S | Su | M | T | W | Th | F | S | Su
1 | Machine Learning Project
1.1 | Kickoff | Kick off meeting to set expextions, roles, and plan |  | 2023-01-24 | 2023-01-24 | 0
1.2 | Data Selection | All team members slect datasets that might work for our project. WE will compare the datasets and vote on which data set is best for our usecase and project | All | 2023-01-25 | 2023-01-28 | 3
1.3 | Github-Setup | Setting up the github repository. Setting up kanban board. Training team members how to use it. | Project Manager | 2023-01-24 | 2023-01-29 | 5
1.4 | Pre-processing data | Cleaning the data and giving team members a clean dataset | Data Analyst | 2023-01-28 | 2023-02-05 | 8
1.5 | Testing of clean data | Make sure clean data reposity is working. Stress testing of the clean data is required to ensure we have a solid foundation | All | 2023-02-05 | 2023-02-05 | 0
1.6 | Data Set Metrics & Visulizations | Create a set of vislizations, and buisness metrics. Please use a consistent theme and colors that match with the theme | Data Analyst | 2023-02-05 | 2023-02-13 | 8
1.7 | Defined Model Metrics | Define the metrics and model insights required (accuracy, precision, recall, number of clusters, ect) | Buisness Analyst | 2023-02-05 | 2023-02-07 | 2
1.8 | Checkpoint With Team - I | Make sure handoffs are going alright and team is set up for success | Project Manager | 2023-02-06 | 2023-02-06 | 0
1.9 | Modeling - Correlations (predictions, classifications other techniques) | Create models based on use case. Each model is evaluated and compared to other models. Mark down the metrics (accuracy, recall, and precision) for each model used. | Data Scientist | 2023-02-05 | 2023-02-12 | 7
1.10 | Interpretation of metrics | Interpret the results of the metrics, the visulisations, and models. Assignt meaning in a ready to report format. The interpretation, of the models and visulisations should be able to be copy pasted into the report documents. | Buisness Analyst | 2023-02-13 | 2023-02-16 | 3
1.11 | Predicitions/ classifications - Communication | Write down the predicitons and what the model is indicationg. Use testing data set to predict | Data Scientist | 2023-02-12 | 2023-02-14 | 2
1.12 | Predicitions Visulization | Visualise the predictions if applicable. Work with data analysts to understand packages and asthetic | Data Scientist | 2023-02-14 | 2023-02-16 | 2
1.13 | Data Visulization Validation | Make sure vuisulizations are looking good, with the right colors and approriate for the use case | Data Analyst | 2023-02-16 | 2023-02-17 | 1
1.14 | Buisness Case - Outline | Creating the buisness value, purpose and underlinying reasons for doing the project | Product Manager | 2023-01-28 | 2023-02-02 | 5
1.15 | Buisness Case - key predictors | draft busienss case based on the outline | Product Manager | 2023-02-02 | 2023-02-06 | 4
1.16 | Deck & Report Theme | create report theme(colors, basic branding ect) | Buisness Analyst | 2023-02-04 | 2023-02-08 | 4
1.17 | Report - Draft #1 | draft #1 of the report | Product Manager | 2023-02-06 | 2023-02-10 | 4
1.18 | Report - Draft #2 | draft #2 of the report | Product Manager | 2023-02-10 | 2023-02-14 | 4
1.2 | Report - Homogenization | smooth over the report for a consistent voice | Project Manager | 2023-02-14 | 2023-02-15 | 1
1.21 | Report- Review | review | All | 2023-02-15 | 2023-02-16 | 1
1.22 | Report- Submit | submit the project | Project manager | 2023-02-16 | 2023-02-16 | 0
1.23 | Checkpoint With Team - II | Make sure handoffs are going alright and team is set up for success | Project Manager | 2023-02-06 | 2023-02-06 | 0
1.24 | Presentation Deck Draft & Design | Design the presentation deck | Project Manager | 2023-02-05 | 2023-02-11 | 6
1.25 | Presentation Deck Finish | Finsih the presentation deck with visuals | Product Manager | 2023-02-11 | 2023-02-14 | 3
1.26 | Checkpoint With Team - III | Make sure handoffs are going alright and team is set up for success | Project Manager | 2023-02-14 | 2023-02-14 | 0
1.27 | Checkpoint | Check in with the team | Project Manager | 2023-02-16 | 2023-02-16 | 0
1.28 | Presentation Practice | Practice the presentation | All | 2023-02-16 | 2023-02-18 | 2
1.28 | Presentation- Execution | execute the presentation | All | 2023-02-17 | 2023-02-17 | 0
1.29 | Buffer |  |  | 2023-02-17 | 2023-02-19 | 2

## Background Data
1 | Su | Data Analyst | Month(s)
2 | M | Data Scientist | Week(s)
3 | T | Buisness Analyst | Day(s)
4 | W | Product Manager
5 | Th | Project Manager
6 | F | All
7 | S